## Sheet1
Task | Planned Effort (hrs) | Actual Effort (hrs)
Define Project Goals | 5 | 5
Requirements Evaluation | 8 | 9
Initial Requirements | 6 | 5
Detailed Requirements | 10 | 11
Identify Stakeholders | 4 | 4
Identify Tools & Technologies | 6 | 7
Project Budget | 5 | 5
Project Schedule | 6 | 7
Form Project Team | 4 | 5
Communication | 5 | 6
Risk Management | 6 | 7
Feasibility | 2 | 3
Quality Management | 2 | 3
Design System Authentication | 10 | 11
Develop Prototype | 14 | 15
Review & Approve Prototype | 6 | 5
Design System Architecture | 15 | 14
Design Database Schema | 12 | 13
UI/UX Design | 13 | 14
OOAD Diagrams | 8 | 7
UI/UX & OOAD Design Feedback | 6 | 7
Design Document Creation | 10 | 8
Program Feature | 28 | 30
Backend Development | 40 | 42
Frontend Development | 36 | 34
Database Connection | 28 | 29
Security Feature | 24 | 23
Unit Testing | 22 | 23
Version Control | 20 | 17
Requirement Analysis | 10 | 11
Test Case Development | 16 | 15
Test Execution | 21 | 20
Test Report | 10 | 11
Deployment Plan | 6 | 5
System Handover | 5 | 6
Feedback | 6 | 5
Documentation | 8 | 9 |  | BAC | 521
Issue Patches & Updates | 6 |  |  | BCWS | 457
Prepare Product Launch Plan | 8 |  |  | BCWP | 443
Market Analysis | 6 |  |  | ACWP | 451
Create Demo Videos/Promos | 7
Email Marketing | 4
Social Media Marketing | 6
Content Writing for Website | 5
Feedback Analysis | 8 |  | Scheduled Task | Till Task 40
Setup Support Channels | 8
Schedule Periodic Updates | 6
Maintenance | 7
Training | 7
| 521 | 451