## Sheet1
Risks | Category | Probability | Impact | RMMM
Size estimate may be significantly low | PS | 60% | 2 | Conduct detailed size estimation using historical data and expert judgment; review regularly.
Larger number of users than planned | PS | 30% | 3 | Perform scalability testing; design architecture for scalability from the start.
Less reuse than planned | PS | 70% | 2 | Identify reusable components early; prepare for backup development resources.
End-users resist system | BU | 40% | 3 | Include users in design & testing; conduct change management training and awareness campaigns.
Delivery deadline will be tightened | BU | 50% | 2 | Prioritize core features; apply agile/iterative delivery; build contingency time into schedule.
Funding will be lost | CU | 40% | 1 | Engage stakeholders; communicate progress frequently; prepare a minimum viable version.
Customer will change requirements | PS | 80% | 2 | Use flexible/agile methods; define change control process; include buffer in planning.
Technology will not meet expectations | TE | 30% | 1 | Evaluate technology early via prototypes or PoC; have backup options.
Lack of training on tools | DE | 80% | 3 | Provide early training and documentation; assign experienced mentors.
Staff inexperienced | ST | 30% | 2 | Assign mentors; conduct skill development sessions; adjust tasks to experience levels.
Staff turnover will be high | ST | 60% | 2 | Maintain knowledge base; apply pair programming; ensure proper documentation.
Delay in UI/UX delivery due to design iteration | TE | 50% | 2 | Conduct early UI prototyping; freeze design specs before development starts.
Version control conflict | DE | 60% | 3 | Define strict version control guidelines; use code reviews and CI/CD.
Test coverage is not sufficient | ST | 75% | 3 | Enforce test-driven development; define test coverage benchmarks; perform regular audits.
Incomplete marketing assets before launch | BU | 50% | 3 | Align marketing and dev teams early; create a shared launch checklist and timeline.
Third-party API (e.g. Weather, Maps) fails or changes | DE | 50% | 2 | Monitor API status; have fallback mechanisms; cache critical data.
Loss of data | DE | 60% | 3 | Implement regular backups; use transactional DB and disaster recovery plan.
Improper authentication and access control | SE | 70% | 2 | Apply secure coding standards; conduct regular security audits and penetration tests.
Vulnerability to SQL injection or XSS attacks | DE | 60% | 1 | Use input validation and sanitization; perform code reviews; apply security testing tools.
Weak password storage practices | SE | 50% | 2 | Use secure hashing (e.g., bcrypt); enforce password policies and salting.
Poorly configured third-party services/APIs | TE | 50% | 2 | Use secure and tested integration; monitor logs; set alerts for failures or misuse.
Lack of user session timeout | SE | 40% | 3 | Implement session timeout policies; monitor session activities.
Deployment without security testing | ST | 50% | 2 | Make security testing mandatory in the CI/CD pipeline; use static/dynamic analysis tools.
1 - Catastrophic
2 - Critical
3 - Marginal
4 - Negligible